## Read Me
NuVue — Strategic Fidelity QA & Launch Readiness
Gold-standard Foundation QA workbook. This demonstration carries approved requirements into QA while preserving the distinction between expected state and actual implementation evidence.
Purpose | Confirm that the implementation reflects the approved strategy and requirements, that the build works technically, and that unresolved risks are explicit before a human launch decision.
Demo boundary | NuVue does not have a completed production build in this demo. Therefore actual implementation observations are intentionally marked NOT TESTED — DEMO. The workbook demonstrates the QA structure without manufacturing passes.
Strategic Fidelity QA | Asks: Did we build what the approved strategy required?
Technical QA | Asks: Does the implementation function correctly across the approved technical scope?
Launch Readiness | Asks: Are blockers, material issues, approvals, dependencies, and accepted limitations resolved enough for a human to authorize launch?
Severity | Blocking = prevents required function or creates unacceptable launch risk. Material = should be resolved before launch unless explicitly accepted. Minor = does not prevent launch. Enhancement = outside required launch state or potentially outside scope.
Status rule | PASS requires evidence. NOT TESTED, BLOCKED, FAIL, or INSUFFICIENT EVIDENCE are valid states. AI should not fill unknowns with a pass.
Source relationship | This workbook is generated from approved Foundation requirements such as the Integrated Site Architecture, page briefs, copy, creative brief, development handoff, measurement requirements, and client decisions.
Core rules
EXPECTED_STATE != OBSERVED_STATE
PASS_REQUIRES_EVIDENCE
NOT_TESTED != PASS
AI_MAY_FLAG_QA_ISSUES
AI_MAY_NOT_APPROVE_QA
STRATEGIC_FIDELITY_QA != TECHNICAL_QA
LAUNCH_REQUIRES_HUMAN_AUTHORIZATION
ACCEPTED_LIMITATION_REQUIRES_OWNER_AND_APPROVAL

## Launch Readiness
Launch Readiness
Human launch authorization gate. Demo states remain not tested unless supported by source evidence.
Gate | Required State | Current Demo State | Status | Severity if Unresolved | Owner | Evidence / Link | Decision / Notes
Strategic Fidelity QA | All material strategic requirements reviewed; blockers resolved or explicitly accepted. | NOT TESTED — DEMO | NOT TESTED | Blocking | Strategist
Technical QA | Approved technical scope validated. | NOT TESTED — DEMO | NOT TESTED | Blocking | Lead Developer
Approved Site Architecture | Final page inventory, navigation, URLs, redirects, metadata, and schema approved. | Source workbook is DRAFT — HUMAN REVIEW | BLOCKED | Blocking | Strategist + Client |  | Architecture cannot be treated as launch-ready while draft.
Approved Copy | Final client-approved copy implemented. | Gold-Standard draft exists; final approval not evidenced. | BLOCKED | Material | Strategist + Client
Approved Design | Final approved design exists and was implemented. | No approved production design in demo. | BLOCKED | Blocking | Designer + Client
Forms / CRM | Required forms submit and route correctly. | NOT TESTED — DEMO | NOT TESTED | Blocking | Developer + Client
Measurement | Approved analytics events and CRM progression validated. | NOT TESTED — DEMO | NOT TESTED | Material | Measurement Owner
Redirects | Required redirects tested and unresolved retire targets resolved. | 74 draft redirect records exist in architecture workbook. | BLOCKED | Material | Developer + Strategist
Claims / Proof | All live claims, logos, case evidence, and guarantee language approved. | Proof dependencies remain open in demo. | BLOCKED | Material | Strategist + Client
Accessibility | Relevant automated + human review completed. | NOT TESTED — DEMO | NOT TESTED | Material | Developer / QA
Responsive / Browser | Approved responsive and browser/device scope tested. | NOT TESTED — DEMO | NOT TESTED | Material | Developer / QA
Performance | Required production performance checks complete. | NOT TESTED — DEMO | NOT TESTED | Material | Developer
Known Limitations | Every accepted limitation has owner, impact, approval, and follow-up. | No production limitations evaluated. | NOT TESTED | Material | Project Lead
Client Approval | Required final client approvals recorded. | Not available in demo. | BLOCKED | Blocking | Project Lead + Client
Launch Authorization | Authorized human explicitly approves production launch. | Not available in demo. | BLOCKED | Blocking | Authorized Human
Note on C5: No completed NuVue production build was provided for testing. Do not convert this demo state into a pass.

## Strategic Fidelity QA
Strategic Fidelity QA
Compares approved requirements against the implemented experience. Actual implementation observations remain NOT TESTED — DEMO.
QA ID | Page ID | Page | Requirement Area | Expected State | Observed State | Evidence | Status | Severity | Owner | Resolution / Decision | Human Approval
SF-001 | NUV-P001 | Homepage | Audience Priority | Corporate buyer is visibly primary while individual path remains clear. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-002 | NUV-P001 | Homepage | Buyer Intent | Primary experience supports Solution Aware visitors while adjacent Problem Aware and Product Aware paths remain coherent. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-003 | NUV-P001 | Homepage | Page Objective | Establish relevance, route corporate and individual buyers, communicate the three-pillar offer, surface proof, and create appropriate next actions. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-004 | NUV-P001 | Homepage | Primary CTA | Primary CTA is Request a Consultation and remains visually primary. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-005 | NUV-P001 | Homepage | Secondary CTA | Secondary path is Take the Self-Assessment / For Myself and does not compete with the primary action. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-006 | NUV-P001 | Homepage | Three-Pillar Architecture | Sales Development, Leadership & Executive Coaching, and Business Acumen are clearly represented as one coherent system. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-007 | NUV-P001 | Homepage | Proof | Approved proof appears close to claims and buyer doubts; unsupported proof is absent. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-008 | NUV-P001 | Homepage | Messaging POV | The sustained-learning point of view is visible and not reduced to generic service copy. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-009 | NUV-P001 | Homepage | Measurement | Required buyer-path and conversion interactions are implemented and trackable. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-010 | NUV-P001 | Homepage | Discoverability | Approved metadata, internal links, and valid schema are implemented without overclaiming. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-011 | NUV-P001 | Homepage | Architecture / Page Role | Page exists at /; purpose is 'Establish relevance, route corporate and individual buyers, communicate the three-pillar offer, surface proof, and create appropriate next actions.'; primary intent is 'Solution Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-012 | NUV-P002 | For Organizations | Architecture / Page Role | Page exists at /solutions-for-organizations/; purpose is 'Help enterprise buyers evaluate NuVue as a development partner and progress toward a qualified consultation.'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-013 | NUV-P003 | For Sales Professionals | Architecture / Page Role | Page exists at /solutions-for-professionals/; purpose is 'Help individual professionals identify the right training path and progress toward seminar or program action.'; primary intent is 'Product Aware / Most Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-014 | NUV-P004 | Curriculum Overview | Architecture / Page Role | Page exists at /curriculum/; purpose is '3-pillar landing page replacing deep nested menus'; primary intent is 'Solution Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-015 | NUV-P005 | Sales (Pillar) | Architecture / Page Role | Page exists at /curriculum/sales/; purpose is 'Pillar landing page - Sales Curriculum'; primary intent is 'Solution Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-016 | NUV-P006 | Counselor Salesperson (CSP) | Architecture / Page Role | Page exists at /curriculum/sales/counselor-salesperson/; purpose is 'Core methodology page — consultative selling approach, enhanced messaging'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-017 | NUV-P007 | Counselor Prospecting | Architecture / Page Role | Page exists at /curriculum/sales/counselor-prospecting/; purpose is 'Existing program, new URL path'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-018 | NUV-P008 | Selling in a Virtual Environment | Architecture / Page Role | Page exists at /curriculum/sales/selling-in-a-virtual-environment/; purpose is 'TBD'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-019 | NUV-P009 | Mastering Successful Presentations | Architecture / Page Role | Page exists at /curriculum/sales/presentations/; purpose is 'Existing program, shortened URL'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-020 | NUV-P010 | Versatile Salesperson | Architecture / Page Role | Page exists at /curriculum/sales/versatile-salesperson/; purpose is 'Existing program, new URL path'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-021 | NUV-P011 | Selling to the Generations | Architecture / Page Role | Page exists at /curriculum/sales/selling-to-the-generations/; purpose is 'Existing program, new URL path'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-022 | NUV-P012 | Turning Information into Sales | Architecture / Page Role | Page exists at /curriculum/sales/turning-information-into-sales/; purpose is 'Existing program, new URL path'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-023 | NUV-P013 | Negotiating to Yes | Architecture / Page Role | Page exists at /curriculum/sales/negotiating-to-yes/; purpose is 'Existing program, new URL path'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-024 | NUV-P014 | Time Management for Salespeople | Architecture / Page Role | Page exists at /curriculum/sales/time-management/; purpose is 'Existing program, new URL path'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-025 | NUV-P015 | Coaching the Counselor Salesperson | Architecture / Page Role | Page exists at /curriculum/sales/coaching-the-counselor-salesperson/; purpose is 'Existing program, new URL path'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-026 | NUV-P016 | Sales Advantage Series | Architecture / Page Role | Page exists at /curriculum/sales/sales-advantage-series/; purpose is 'Existing program, new URL path'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-027 | NUV-P017 | Trade Show Selling | Architecture / Page Role | Page exists at /curriculum/sales/trade-show-selling/; purpose is 'Existing program, new URL path'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-028 | NUV-P018 | Value-Added Selling | Architecture / Page Role | Page exists at /curriculum/sales/value-added-selling/; purpose is 'Existing program, new URL path'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-029 | NUV-P019 | Sales Assessments | Architecture / Page Role | Page exists at /curriculum/sales/sales-assessments/; purpose is 'Existing'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-030 | NUV-P020 | Leadership (Pillar) | Architecture / Page Role | Page exists at /curriculum/leadership/; purpose is 'Pillar landing — 18+ workshops + executive coaching combined'; primary intent is 'Solution Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-031 | NUV-P021 | Executive Coaching | Architecture / Page Role | Page exists at /curriculum/leadership/executive-coaching/; purpose is 'Dedicated page — new managers to C-suite. Moved from /coaching/'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-032 | NUV-P022 | Building Relationship Versatility | Architecture / Page Role | Page exists at /curriculum/leadership/building-relationship-versatility/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-033 | NUV-P023 | Coaching for Performance | Architecture / Page Role | Page exists at /curriculum/leadership/coaching-for-performance/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-034 | NUV-P024 | Coaching for Sales Performance | Architecture / Page Role | Page exists at /curriculum/leadership/coaching-for-sales-performance/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-035 | NUV-P025 | Communicating with Purpose | Architecture / Page Role | Page exists at /curriculum/leadership/communicating-with-purpose/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-036 | NUV-P026 | Managing Conflict | Architecture / Page Role | Page exists at /curriculum/leadership/managing-conflict/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-037 | NUV-P027 | Managing Styles in Conflict | Architecture / Page Role | Page exists at /curriculum/leadership/managing-styles-in-conflict/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-038 | NUV-P028 | Meeting Leadership Challenges | Architecture / Page Role | Page exists at /curriculum/leadership/meeting-leadership-challenges/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-039 | NUV-P029 | Delegating with Confidence | Architecture / Page Role | Page exists at /curriculum/leadership/delegating-with-confidence/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-040 | NUV-P030 | Leading from Within | Architecture / Page Role | Page exists at /curriculum/leadership/leading-from-within/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-041 | NUV-P031 | Leading in Challenging Times | Architecture / Page Role | Page exists at /curriculum/leadership/leading-in-challenging-times/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-042 | NUV-P032 | The Leader-Manager | Architecture / Page Role | Page exists at /curriculum/leadership/the-leader-manager/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-043 | NUV-P033 | Creating a Culture of Engagement | Architecture / Page Role | Page exists at /curriculum/leadership/creating-a-culture-of-engagement/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-044 | NUV-P034 | Getting to Yes | Architecture / Page Role | Page exists at /curriculum/leadership/getting-to-yes/; purpose is 'Existing program, shortened URL'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-045 | NUV-P035 | Global Effectiveness | Architecture / Page Role | Page exists at /curriculum/leadership/global-effectiveness/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-046 | NUV-P036 | Motivating for Results | Architecture / Page Role | Page exists at /curriculum/leadership/motivating-for-results/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-047 | NUV-P037 | Leading for Growth | Architecture / Page Role | Page exists at /curriculum/leadership/leading-for-growth/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-048 | NUV-P038 | Interviewing for Selection | Architecture / Page Role | Page exists at /curriculum/leadership/interviewing-for-selection/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-049 | NUV-P039 | Consulting with Clients | Architecture / Page Role | Page exists at /curriculum/leadership/consulting-with-clients/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-050 | NUV-P040 | Work-Life Balance | Architecture / Page Role | Page exists at /curriculum/leadership/work-life-balance/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-051 | NUV-P041 | Working Styles / Social Styles | Architecture / Page Role | Page exists at /curriculum/leadership/working-styles/; purpose is 'Existing program, shortened URL'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-052 | NUV-P042 | Building High-Performance Teams | Architecture / Page Role | Page exists at /curriculum/leadership/building-high-performance-teams/; purpose is 'Moved from Team Building to Leadership pillar'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-053 | NUV-P043 | Virtual Coaching | Architecture / Page Role | Page exists at /curriculum/leadership/virtual-coaching/; purpose is 'Moved from /coaching/ to Leadership pillar'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-054 | NUV-P044 | Leadership Assessments | Architecture / Page Role | Page exists at /curriculum/leadership/leadership-assessments/; purpose is 'Existing'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-055 | NUV-P045 | ARA Navigator 360 | Architecture / Page Role | Page exists at /curriculum/leadership/ara-navigator-360/; purpose is 'Existing, shortened URL'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-056 | NUV-P046 | Business Acumen (Pillar) | Architecture / Page Role | Page exists at /curriculum/business-acumen/; purpose is 'Pillar landing — Income¦Outcome + financial literacy programs'; primary intent is 'Solution Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-057 | NUV-P047 | Income¦Outcome Business Simulation | Architecture / Page Role | Page exists at /curriculum/business-acumen/income-outcome/; purpose is 'Featured program — financial literacy simulation, enhanced positioning'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-058 | NUV-P048 | Finance for Sales Professionals | Architecture / Page Role | Page exists at /curriculum/business-acumen/finance-for-sales-professionals/; purpose is 'Existing program'; primary intent is 'Product Aware / Most Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-059 | NUV-P049 | Finance for Managers & Executives | Architecture / Page Role | Page exists at /curriculum/business-acumen/finance-for-managers-and-executives/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-060 | NUV-P050 | Finance for Everyone | Architecture / Page Role | Page exists at /curriculum/business-acumen/finance-for-everyone/; purpose is 'Existing program'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-061 | NUV-P051 | Team Building | Architecture / Page Role | Page exists at [approved URL pending]; purpose is 'Programs absorbed into Leadership pillar'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-062 | NUV-P052 | Industries We Serve | Architecture / Page Role | Page exists at /industries/; purpose is 'Problem-first landing pages for each vertical'; primary intent is 'Solution Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-063 | NUV-P053 | Agriculture | Architecture / Page Role | Page exists at /industries/agriculture/; purpose is 'CSP Ag Edition featured, BASF expertise, ag-specific case studies'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-064 | NUV-P054 | Manufacturing | Architecture / Page Role | Page exists at /industries/manufacturing/; purpose is 'Industry-specific messaging and case studies'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-065 | NUV-P055 | Insurance & Financial Services | Architecture / Page Role | Page exists at /industries/insurance-financial-services/; purpose is 'Combined vertical with tailored content'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-066 | NUV-P056 | Turf & Horticulture | Architecture / Page Role | Page exists at /industries/turf-horticulture/; purpose is 'Existing vertical'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-067 | NUV-P057 | Sales & Services | Architecture / Page Role | Page exists at /industries/sales-and-services/; purpose is 'Existing vertical'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-068 | NUV-P058 | Healthcare, Science & Biotech | Architecture / Page Role | Page exists at /industries/healthcare-science-biotech/; purpose is 'Existing vertical'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-069 | NUV-P059 | Resources | Architecture / Page Role | Page exists at /resources/; purpose is 'Content hub for SEO/AEO visibility'; primary intent is 'Symptom Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-070 | NUV-P060 | Assessments | Architecture / Page Role | Page exists at /resources/assessments/; purpose is 'Assessment tools hub'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-071 | NUV-P061 | Blog | Architecture / Page Role | Page exists at /resources/blog/; purpose is 'Revived content engine — editorial calendar per audit'; primary intent is 'Symptom Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-072 | NUV-P062 | Articles | Architecture / Page Role | Page exists at /resources/articles/; purpose is 'Existing content'; primary intent is 'Symptom Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-073 | NUV-P063 | Podcasts | Architecture / Page Role | Page exists at /resources/podcasts/; purpose is 'Existing content'; primary intent is 'Symptom Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-074 | NUV-P064 | Case Studies | Architecture / Page Role | Page exists at /resources/case-studies/; purpose is 'Industry-specific with before/after metrics ($400K avg increase)'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-075 | NUV-P065 | Client Testimonials | Architecture / Page Role | Page exists at /resources/testimonials/; purpose is 'Existing content'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-076 | NUV-P066 | Public Seminars | Architecture / Page Role | Page exists at /public-seminars/; purpose is 'Top-level nav item — dates, pricing ($850-$1,450), Company Name field on forms'; primary intent is 'Product Aware / Most Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-077 | NUV-P067 | Counselor Salesperson | Architecture / Page Role | Page exists at /public-seminars/counselor-salesperson/; purpose is 'Individual buyer focused public seminar landing page -> select date to purchase'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-078 | NUV-P068 | Negotiationg To Yes | Architecture / Page Role | Page exists at /public-seminars/negotiating-to-yes/; purpose is 'Individual buyer focused public seminar landing page -> select date to purchase'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-079 | NUV-P069 | Building Relationship Versatility | Architecture / Page Role | Page exists at /public-seminars/building-relationship-versatility/; purpose is 'Individual buyer focused public seminar landing page -> select date to purchase'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-080 | NUV-P070 | About NuVue | Architecture / Page Role | Page exists at /about/; purpose is 'Trust-building section'; primary intent is 'Product Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-081 | NUV-P071 | Our Approach | Architecture / Page Role | Page exists at /about/our-approach/; purpose is 'Methodology depth — LTNS, Wilson Learning, proprietary frameworks, E-E-A-T'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-082 | NUV-P072 | Meet Our Team | Architecture / Page Role | Page exists at /about/team/; purpose is 'Steve's 35 years + BASF credentials surfaced'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-083 | NUV-P073 | Join Our Team | Architecture / Page Role | Page exists at /about/careers/; purpose is 'Existing page, new URL path'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-084 | NUV-P074 | Request a Consultation | Architecture / Page Role | Page exists at /request-consultation/; purpose is 'Convert qualified corporate interest into a structured consultation request with usable CRM context.'; primary intent is 'Most Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-085 | NUV-P075 | Apply for the CSP Guarantee | Architecture / Page Role | Page exists at /apply-guarantee/; purpose is 'Qualify enterprise buyers for the CSP Guarantee and route eligible interest into the appropriate sales process.'; primary intent is 'Most Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-086 | NUV-P076 | Contact Us | Architecture / Page Role | Page exists at /contact/; purpose is 'Enhanced with Zoho CRM integration'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-087 | NUV-P077 | Self-Assessment Quiz | Architecture / Page Role | Page exists at /quiz/; purpose is '"What's Holding Your Sales Team Back?" — transitional CTA, lead capture'; primary intent is 'Problem Aware'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-088 | NUV-P078 | Thank You / Confirmation | Architecture / Page Role | Page exists at /thank-you/; purpose is 'Post-conversion page'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-089 | NUV-P079 | Store | Architecture / Page Role | Page exists at /store/; purpose is 'Expanded WooCommerce — seminars, LTNS, curriculum subscriptions'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-090 | NUV-P080 | Cart | Architecture / Page Role | Page exists at /cart/; purpose is 'Existing'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-091 | NUV-P081 | Checkout | Architecture / Page Role | Page exists at /checkout/; purpose is 'Existing'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-092 | NUV-P082 | My Account | Architecture / Page Role | Page exists at /my-account/; purpose is 'Existing'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-093 | NUV-P083 | My Bookings | Architecture / Page Role | Page exists at /my-bookings/; purpose is 'Existing'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-094 | NUV-P084 | Privacy Policy | Architecture / Page Role | Page exists at /privacy-policy/; purpose is 'Existing'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-095 | NUV-P085 | Communication Preferences | Architecture / Page Role | Page exists at /communication-preferences/; purpose is 'Existing'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-096 | NUV-P086 | Learning That Never Stops® Sign Up | Architecture / Page Role | Page exists at [approved URL pending]; purpose is 'Repositioned as retention & expansion tool, not just reinforcement'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-097 | NUV-P087 | Westlink 6th Man | Architecture / Page Role | Page exists at [approved URL pending]; purpose is 'Campaign-specific — archive or redirect'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-098 | NUV-P088 | Marketing Signup | Architecture / Page Role | Page exists at [approved URL pending]; purpose is 'Replace with new conversion pages'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
SF-099 | NUV-P089 | CSP Training Landing Page | Architecture / Page Role | Page exists at [approved URL pending]; purpose is 'Replace with new CSP page structure'; primary intent is 'TBD — HUMAN REVIEW'. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
Note on F5: Observed state requires real implementation evidence such as staging URL, screenshot, analytics debug, CRM record, or human review.

## Technical QA
Technical QA
Functional and technical validation. The sample provides test definitions only; no production passes are manufactured.
QA ID | Category | Test | Expected Result | Observed Result | Evidence | Status | Severity | Owner | Resolution | Retest Status
TQ-001 | Responsive | Homepage / priority templates | Critical content, hierarchy, CTAs, and navigation remain usable across approved viewport sizes. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-002 | Navigation | Global navigation | Primary, utility, mobile, and footer navigation routes work and match approved architecture. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-003 | Links | Internal links | No broken internal links; destinations match approved architecture. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-004 | Forms | Consultation form | Validation, submission, CRM routing, confirmation, and error states work as approved. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-005 | Forms | Guarantee / application | Eligibility flow and routing match approved requirements where implemented. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-006 | CRM | Lead routing | Required fields, source context, lifecycle / pipeline mapping, and ownership work. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-007 | Analytics | GA4 / GTM events | Approved events fire once with correct names and parameters. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-008 | SEO | Metadata | Approved title, meta description, canonical, headings, and indexing controls are implemented. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-009 | Schema | Structured data | Only approved schema matching actual page content is deployed; validation passes. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-010 | Redirects | 301 redirects | Approved redirect map resolves correctly with no loops or chains. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-011 | Accessibility | Keyboard / focus | All required interactive elements are keyboard operable with visible focus. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-012 | Accessibility | Forms / labels | Labels, instructions, errors, and required states are accessible. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-013 | Accessibility | Images / alt | Meaningful images have appropriate alt; decorative images do not create noise. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-014 | Performance | Core assets | No avoidable oversized images, blocking scripts, or obvious layout instability. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-015 | Browser / Device | Approved scope | Priority flows work across the approved browser/device matrix. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-016 | Migration | Retired / moved pages | No orphaned high-value URLs; retirements follow approved migration logic. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-017 | Content | Placeholders | No lorem ipsum, placeholder results, unapproved claims, or stale draft markers remain. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
TQ-018 | Security | WordPress / access | Approved production configuration, plugin/access practices, and credentials are in place. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA

## Architecture QA
Architecture QA
Validates approved page inventory, URLs, buyer intent, metadata, schema, and migration requirements against implementation.
QA ID | Page ID | Page | Scope / Status | Expected URL | Buyer Intent | Meta Title | Schema | Redirect Requirement | Observed State | Status | Severity | Notes
AQ-001 | NUV-P001 | Homepage | ENHANCED | / | Solution Aware | Sales Training That Guarantees Results ¦ NuVue | Organization, WebSite | NO | NOT TESTED — DEMO | NOT TESTED | Material
AQ-002 | NUV-P002 | For Organizations | NEW | /solutions-for-organizations/ | Product Aware | Sales Training for Teams & Organizations ¦ NuVue | Service, BreadcrumbList | NO — new URL | NOT TESTED — DEMO | NOT TESTED | Material
AQ-003 | NUV-P003 | For Sales Professionals | NEW | /solutions-for-professionals/ | Product Aware / Most Aware | Sales Training for Professionals ¦ NuVue | Service, BreadcrumbList | NO — new URL | NOT TESTED — DEMO | NOT TESTED | Material
AQ-004 | NUV-P004 | Curriculum Overview | RESTRUCTURED | /curriculum/ | Solution Aware | Sales & Leadership Training Curriculum ¦ NuVue | CollectionPage, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-005 | NUV-P005 | Sales (Pillar) | RESTRUCTURED | /curriculum/sales/ | Solution Aware | Sales Development Training Programs ¦ NuVue | CollectionPage, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-006 | NUV-P006 | Counselor Salesperson (CSP) | ENHANCED | /curriculum/sales/counselor-salesperson/ | Product Aware | Counselor Salesperson (CSP) Training ¦ NuVue | Course, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-007 | NUV-P007 | Counselor Prospecting | EXISTS | /curriculum/sales/counselor-prospecting/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-008 | NUV-P008 | Selling in a Virtual Environment | EXISTS | /curriculum/sales/selling-in-a-virtual-environment/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Page objective, Metadata, Schema
AQ-009 | NUV-P009 | Mastering Successful Presentations | EXISTS | /curriculum/sales/presentations/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-010 | NUV-P010 | Versatile Salesperson | EXISTS | /curriculum/sales/versatile-salesperson/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-011 | NUV-P011 | Selling to the Generations | EXISTS | /curriculum/sales/selling-to-the-generations/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-012 | NUV-P012 | Turning Information into Sales | EXISTS | /curriculum/sales/turning-information-into-sales/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-013 | NUV-P013 | Negotiating to Yes | EXISTS | /curriculum/sales/negotiating-to-yes/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-014 | NUV-P014 | Time Management for Salespeople | EXISTS | /curriculum/sales/time-management/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-015 | NUV-P015 | Coaching the Counselor Salesperson | EXISTS | /curriculum/sales/coaching-the-counselor-salesperson/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-016 | NUV-P016 | Sales Advantage Series | EXISTS | /curriculum/sales/sales-advantage-series/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-017 | NUV-P017 | Trade Show Selling | EXISTS | /curriculum/sales/trade-show-selling/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-018 | NUV-P018 | Value-Added Selling | EXISTS | /curriculum/sales/value-added-selling/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-019 | NUV-P019 | Sales Assessments | MOVED | /curriculum/sales/sales-assessments/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-020 | NUV-P020 | Leadership (Pillar) | RESTRUCTURED | /curriculum/leadership/ | Solution Aware | Leadership & Executive Coaching Programs ¦ NuVue | CollectionPage, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-021 | NUV-P021 | Executive Coaching | ENHANCED | /curriculum/leadership/executive-coaching/ | Product Aware | Executive Coaching Services ¦ NuVue | Service, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-022 | NUV-P022 | Building Relationship Versatility | EXISTS | /curriculum/leadership/building-relationship-versatility/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-023 | NUV-P023 | Coaching for Performance | EXISTS | /curriculum/leadership/coaching-for-performance/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-024 | NUV-P024 | Coaching for Sales Performance | EXISTS | /curriculum/leadership/coaching-for-sales-performance/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-025 | NUV-P025 | Communicating with Purpose | EXISTS | /curriculum/leadership/communicating-with-purpose/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-026 | NUV-P026 | Managing Conflict | EXISTS | /curriculum/leadership/managing-conflict/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-027 | NUV-P027 | Managing Styles in Conflict | EXISTS | /curriculum/leadership/managing-styles-in-conflict/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-028 | NUV-P028 | Meeting Leadership Challenges | EXISTS | /curriculum/leadership/meeting-leadership-challenges/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-029 | NUV-P029 | Delegating with Confidence | EXISTS | /curriculum/leadership/delegating-with-confidence/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-030 | NUV-P030 | Leading from Within | EXISTS | /curriculum/leadership/leading-from-within/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-031 | NUV-P031 | Leading in Challenging Times | EXISTS | /curriculum/leadership/leading-in-challenging-times/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-032 | NUV-P032 | The Leader-Manager | EXISTS | /curriculum/leadership/the-leader-manager/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-033 | NUV-P033 | Creating a Culture of Engagement | EXISTS | /curriculum/leadership/creating-a-culture-of-engagement/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-034 | NUV-P034 | Getting to Yes | EXISTS | /curriculum/leadership/getting-to-yes/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-035 | NUV-P035 | Global Effectiveness | EXISTS | /curriculum/leadership/global-effectiveness/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-036 | NUV-P036 | Motivating for Results | EXISTS | /curriculum/leadership/motivating-for-results/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-037 | NUV-P037 | Leading for Growth | EXISTS | /curriculum/leadership/leading-for-growth/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-038 | NUV-P038 | Interviewing for Selection | EXISTS | /curriculum/leadership/interviewing-for-selection/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-039 | NUV-P039 | Consulting with Clients | EXISTS | /curriculum/leadership/consulting-with-clients/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-040 | NUV-P040 | Work-Life Balance | EXISTS | /curriculum/leadership/work-life-balance/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-041 | NUV-P041 | Working Styles / Social Styles | EXISTS | /curriculum/leadership/working-styles/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-042 | NUV-P042 | Building High-Performance Teams | MOVED | /curriculum/leadership/building-high-performance-teams/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-043 | NUV-P043 | Virtual Coaching | EXISTS | /curriculum/leadership/virtual-coaching/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-044 | NUV-P044 | Leadership Assessments | MOVED | /curriculum/leadership/leadership-assessments/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-045 | NUV-P045 | ARA Navigator 360 | EXISTS | /curriculum/leadership/ara-navigator-360/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-046 | NUV-P046 | Business Acumen (Pillar) | RESTRUCTURED | /curriculum/business-acumen/ | Solution Aware | Business Acumen & Financial Literacy Training ¦ NuVue | CollectionPage, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-047 | NUV-P047 | Income¦Outcome Business Simulation | ENHANCED | /curriculum/business-acumen/income-outcome/ | Product Aware | Income¦Outcome Business Simulation ¦ NuVue | Course, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-048 | NUV-P048 | Finance for Sales Professionals | EXISTS | /curriculum/business-acumen/finance-for-sales-professionals/ | Product Aware / Most Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-049 | NUV-P049 | Finance for Managers & Executives | EXISTS | /curriculum/business-acumen/finance-for-managers-and-executives/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-050 | NUV-P050 | Finance for Everyone | EXISTS | /curriculum/business-acumen/finance-for-everyone/ | Product Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-051 | NUV-P051 | Team Building | EXISTS |  | TBD — HUMAN REVIEW |  |  |  | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-052 | NUV-P052 | Industries We Serve | ENHANCED | /industries/ | Solution Aware | Industries We Serve ¦ Sales Training ¦ NuVue | CollectionPage, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-053 | NUV-P053 | Agriculture | ENHANCED | /industries/agriculture/ | TBD — HUMAN REVIEW | Agriculture Sales Training ¦ NuVue | Service, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent
AQ-054 | NUV-P054 | Manufacturing | ENHANCED | /industries/manufacturing/ | TBD — HUMAN REVIEW | Manufacturing Sales Training ¦ NuVue | Service, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent
AQ-055 | NUV-P055 | Insurance & Financial Services | ENHANCED | /industries/insurance-financial-services/ | TBD — HUMAN REVIEW | Insurance & Financial Services Sales Training ¦ NuVue | Service, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent
AQ-056 | NUV-P056 | Turf & Horticulture | EXISTS | /industries/turf-horticulture/ | TBD — HUMAN REVIEW | Turf & Horticulture Sales Training ¦ NuVue | Service, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent
AQ-057 | NUV-P057 | Sales & Services | EXISTS | /industries/sales-and-services/ | TBD — HUMAN REVIEW | Sales & Services Industry Training ¦ NuVue | Service, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent
AQ-058 | NUV-P058 | Healthcare, Science & Biotech | EXISTS | /industries/healthcare-science-biotech/ | TBD — HUMAN REVIEW | Healthcare, Science & Biotech Sales Training ¦ NuVue | Service, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent
AQ-059 | NUV-P059 | Resources | RESTRUCTURED | /resources/ | Symptom Aware | Sales Training Resources & Insights ¦ NuVue | CollectionPage, BreadcrumbList |  | NOT TESTED — DEMO | NOT TESTED | Material
AQ-060 | NUV-P060 | Assessments | MOVED | /resources/assessments/ | TBD — HUMAN REVIEW | Free Sales & Leadership Assessments ¦ NuVue | WebPage, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent
AQ-061 | NUV-P061 | Blog | ENHANCED | /resources/blog/ | Symptom Aware | Sales & Leadership Blog ¦ NuVue | Blog, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-062 | NUV-P062 | Articles | EXISTS | /resources/articles/ | Symptom Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-063 | NUV-P063 | Podcasts | EXISTS | /resources/podcasts/ | Symptom Aware |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Metadata, Schema
AQ-064 | NUV-P064 | Case Studies | NEW | /resources/case-studies/ | Product Aware | Sales Training Case Studies & Results ¦ NuVue | CollectionPage, BreadcrumbList | NO — new URL | NOT TESTED — DEMO | NOT TESTED | Material
AQ-065 | NUV-P065 | Client Testimonials | EXISTS | /resources/testimonials/ | Product Aware | Client Testimonials & Reviews ¦ NuVue | WebPage, Review, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-066 | NUV-P066 | Public Seminars | ENHANCED | /public-seminars/ | Product Aware / Most Aware | Public Sales Training Seminars & Dates ¦ NuVue | CollectionPage, BreadcrumbList | NO | NOT TESTED — DEMO | NOT TESTED | Material
AQ-067 | NUV-P067 | Counselor Salesperson | NEW | /public-seminars/counselor-salesperson/ | TBD — HUMAN REVIEW |  |  | NO — new URL | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-068 | NUV-P068 | Negotiationg To Yes | NEW | /public-seminars/negotiating-to-yes/ | TBD — HUMAN REVIEW |  |  | NO — new URL | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-069 | NUV-P069 | Building Relationship Versatility | NEW | /public-seminars/building-relationship-versatility/ | TBD — HUMAN REVIEW |  |  | NO — new URL | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-070 | NUV-P070 | About NuVue | ENHANCED | /about/ | Product Aware | About NuVue ¦ Sales Training Since 2002 | AboutPage, Organization, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-071 | NUV-P071 | Our Approach | NEW | /about/our-approach/ | TBD — HUMAN REVIEW | Our Approach to Sales Training ¦ NuVue | AboutPage, BreadcrumbList | NO — new URL | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent
AQ-072 | NUV-P072 | Meet Our Team | EXISTS | /about/team/ | TBD — HUMAN REVIEW | Meet Our Team ¦ NuVue | AboutPage, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent
AQ-073 | NUV-P073 | Join Our Team | EXISTS | /about/careers/ | TBD — HUMAN REVIEW |  |  | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-074 | NUV-P074 | Request a Consultation | NEW | /request-consultation/ | Most Aware | Request a Sales Training Consultation ¦ NuVue | ContactPage, BreadcrumbList | NO — new URL | NOT TESTED — DEMO | NOT TESTED | Material
AQ-075 | NUV-P075 | Apply for the CSP Guarantee | NEW | /apply-guarantee/ | Most Aware | Apply for the CSP Performance Guarantee ¦ NuVue | WebPage, Offer, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material
AQ-076 | NUV-P076 | Contact Us | EXISTS | /contact/ | TBD — HUMAN REVIEW | Contact NuVue ¦ Sales Training Experts | ContactPage, Organization, BreadcrumbList | YES — 301 | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent
AQ-077 | NUV-P077 | Self-Assessment Quiz | NEW | /quiz/ | Problem Aware | What's Holding Your Sales Team Back? ¦ NuVue | WebPage, Quiz, BreadcrumbList | NO — new URL | NOT TESTED — DEMO | NOT TESTED | Material
AQ-078 | NUV-P078 | Thank You / Confirmation | EXISTS | /thank-you/ | TBD — HUMAN REVIEW |  |  | NO | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-079 | NUV-P079 | Store | ENHANCED | /store/ | TBD — HUMAN REVIEW |  |  | NO | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-080 | NUV-P080 | Cart | EXISTS | /cart/ | TBD — HUMAN REVIEW |  |  | NO | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-081 | NUV-P081 | Checkout | EXISTS | /checkout/ | TBD — HUMAN REVIEW |  |  | NO | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-082 | NUV-P082 | My Account | EXISTS | /my-account/ | TBD — HUMAN REVIEW |  |  | NO | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-083 | NUV-P083 | My Bookings | EXISTS | /my-bookings/ | TBD — HUMAN REVIEW |  |  | NO | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-084 | NUV-P084 | Privacy Policy | EXISTS | /privacy-policy/ | TBD — HUMAN REVIEW |  |  | NO | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-085 | NUV-P085 | Communication Preferences | EXISTS | /communication-preferences/ | TBD — HUMAN REVIEW |  |  | NO | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-086 | NUV-P086 | Learning That Never Stops® Sign Up | EXISTS |  | TBD — HUMAN REVIEW |  |  |  | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-087 | NUV-P087 | Westlink 6th Man | EXISTS |  | TBD — HUMAN REVIEW |  |  |  | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-088 | NUV-P088 | Marketing Signup | EXISTS |  | TBD — HUMAN REVIEW |  |  |  | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-089 | NUV-P089 | CSP Training Landing Page | EXISTS |  | TBD — HUMAN REVIEW |  |  |  | NOT TESTED — DEMO | NOT TESTED | Material | Buyer intent, Metadata, Schema
AQ-090 | NUV-P090 | Public Seminars 2 (duplicate) | RETIRE |  | Product Aware / Most Aware |  |  | YES — target required | NOT TESTED — DEMO | NOT TESTED | Material | Redirect target
AQ-091 | NUV-P091 | Customer Service section | RETIRE |  | N/A — RETIRE |  |  | YES — target required | NOT TESTED — DEMO | NOT TESTED | Material | Redirect target
AQ-092 | NUV-P092 | Coaching | RETIRE |  | N/A — RETIRE |  |  | YES — target required | NOT TESTED — DEMO | NOT TESTED | Material | Redirect target
AQ-093 | NUV-P093 | Sales Curriculum Guide | RETIRE |  | N/A — RETIRE |  |  | YES — target required | NOT TESTED — DEMO | NOT TESTED | Material | Redirect target
AQ-094 | NUV-P094 | eLearning section | RETIRE |  | N/A — RETIRE |  |  | YES — target required | NOT TESTED — DEMO | NOT TESTED | Material | Redirect target
AQ-095 | NUV-P095 | Events | RETIRE |  | N/A — RETIRE |  |  | YES — target required | NOT TESTED — DEMO | NOT TESTED | Material | Redirect target
AQ-096 | NUV-P096 | Logos | RETIRE |  | N/A — RETIRE |  |  | YES — target required | NOT TESTED — DEMO | NOT TESTED | Material | Redirect target
AQ-097 | NUV-P097 | Locations | RETIRE |  | N/A — RETIRE |  |  | YES — target required | NOT TESTED — DEMO | NOT TESTED | Material | Redirect target
AQ-098 | NUV-P098 | Categories | RETIRE |  | N/A — RETIRE |  |  | YES — target required | NOT TESTED — DEMO | NOT TESTED | Material | Redirect target
AQ-099 | NUV-P099 | Tags | RETIRE |  | N/A — RETIRE |  |  | YES — target required | NOT TESTED — DEMO | NOT TESTED | Material | Redirect target

## Content & Proof QA
Content & Proof QA
Checks approved copy, claims, evidence, logos, testimonials, guarantee language, and proof placement.
QA ID | Page / Asset | Check Type | Expected State | Observed State | Source / Evidence | Status | Severity | Owner | Resolution
CP-001 | Homepage | Copy Fidelity | Final implemented copy matches approved client copy except approved production edits. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
CP-002 | Homepage | Buyer Intent / CTA | Message depth, proof, and CTA sequence match approved buyer intent. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
CP-003 | Homepage | 24+ Years Claim | Current founding reference supports the live claim. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
CP-004 | Homepage | 101+ Workshops Claim | Current inventory supports the live count. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
CP-005 | Homepage | ROI Evidence | Every live ROI result is traceable to an approved evaluation / case source. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
CP-006 | Homepage | Client Logos | Every displayed client logo has current permission. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
CP-007 | Homepage | Guarantee | Terms, eligibility, thresholds, annual capacity, and qualification language match current approved documentation. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
CP-008 | Homepage | Testimonials | Quotes use approved wording and attribution. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
CP-009 | Sitewide | Unsupported Superlatives | No unsubstantiated 'best', 'only', 'leading', or equivalent claims are live. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA
CP-010 | Sitewide | Placeholder Content | No draft markers, placeholders, or synthetic demo language remain. | NOT TESTED — DEMO |  | NOT TESTED | Material | Strategist / QA

## Measurement QA
Measurement QA
Validates that meaningful events, forms, CRM progression, and known attribution limits are implemented as approved.
QA ID | Journey / Event | Expected Implementation | Observed State | Evidence | Status | Severity | Owner | Notes
MQ-001 | buyer_path_select | For My Team / For Myself selections are captured with path and page context. | NOT TESTED — DEMO |  | NOT TESTED | Material | Measurement Owner
MQ-002 | consultation_cta_click | Consultation CTA clicks capture page and location. | NOT TESTED — DEMO |  | NOT TESTED | Material | Measurement Owner
MQ-003 | consultation_form_start | Form start is recorded without duplicate firing. | NOT TESTED — DEMO |  | NOT TESTED | Material | Measurement Owner
MQ-004 | consultation_form_submit | Successful submission records once and can be linked to CRM outcome where supported. | NOT TESTED — DEMO |  | NOT TESTED | Material | Measurement Owner
MQ-005 | assessment_start | Assessment entry is tracked if the assessment launches. | NOT TESTED — DEMO |  | NOT TESTED | Material | Measurement Owner
MQ-006 | assessment_complete | Completion is tracked with approved result/category where allowed. | NOT TESTED — DEMO |  | NOT TESTED | Material | Measurement Owner
MQ-007 | solution_select | Pillar selections distinguish Sales, Leadership, and Business Acumen. | NOT TESTED — DEMO |  | NOT TESTED | Material | Measurement Owner
MQ-008 | guarantee_interest | Guarantee-interest click is recorded without implying qualification. | NOT TESTED — DEMO |  | NOT TESTED | Material | Measurement Owner
MQ-009 | industry_select | Industry selection identifies the chosen vertical. | NOT TESTED — DEMO |  | NOT TESTED | Material | Measurement Owner
MQ-010 | CRM qualification | Role, company, team size, industry, challenge, and timing fields map as approved. | NOT TESTED — DEMO |  | NOT TESTED | Material | Measurement Owner
MQ-011 | Attribution limitation | Reporting preserves known limitations and does not convert platform attribution into causal ROI. | NOT TESTED — DEMO |  | NOT TESTED | Material | Measurement Owner

## Accessibility QA
Accessibility QA
Supportive accessibility QA structure. Automated tools may assist, but human review remains required.
QA ID | Area | Expected State | Observed State | Evidence | Status | Severity | Owner | Resolution
AC-001 | Semantic structure | Appropriate landmarks, headings, lists, links, buttons, and form semantics. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
AC-002 | Keyboard | All interactive elements operable by keyboard. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
AC-003 | Focus | Visible focus states are present and logical. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
AC-004 | Contrast | Text and controls meet approved contrast requirements. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
AC-005 | Forms | Programmatic labels, clear errors, instructions, and required states. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
AC-006 | Images | Meaningful alt text; decorative images handled appropriately. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
AC-007 | Motion | Reduced-motion preferences respected where motion exists. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
AC-008 | Zoom / Reflow | Content remains usable at approved zoom / reflow conditions. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
AC-009 | Link Purpose | Link and button labels communicate destination or action. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA
AC-010 | Human Review | Relevant templates and critical flows receive human accessibility review. | NOT TESTED — DEMO |  | NOT TESTED | Material | Developer / QA

## Issue Register
Issue Register
Central register for QA issues, accepted limitations, owners, and resolution status.
Issue ID | Source QA | Page / Area | Issue | Severity | Status | Owner | Due / Decision Date | Resolution | Accepted Limitation? | Approved By | Evidence / Link
ISS-001 | Launch Readiness | Architecture | Integrated Site Architecture remains DRAFT — HUMAN REVIEW. | Blocking | OPEN | Strategist + Client |  | Approve architecture before treating it as implementation source. | No
ISS-002 | Launch Readiness | Design | No approved production homepage design exists in demo. | Blocking | OPEN | Designer + Client |  | Design approval required before final implementation QA. | No
ISS-003 | Launch Readiness | Claims / Proof | Guarantee and ROI proof dependencies are unresolved in demo context. | Material | OPEN | NuVue + Strategist |  | Resolve sources, terms, permissions, and approved wording. | No
ISS-004 | Redirects | Migration | Retired pages with unresolved redirect targets cannot be launch-ready. | Material | OPEN | Strategist + Developer |  | Approve redirect targets based on relevance and migration logic. | No

## Approvals
Approvals
Human approval record. AI may prepare this register but may not approve any gate.
Approval | Required Approver | Required Before | Current State | Approval Date | Evidence / Link | Notes
Integrated Site Architecture | Strategist + Client | Copy / Design / Development finalization | PENDING
Final Messaging / Copy | Strategist + Client | Implementation / launch | PENDING
Final Design | Designer / Strategist + Client | Development finalization | PENDING
Technical Architecture | Lead Developer | Production readiness | PENDING
Claim / Guarantee Wording | NuVue authorized approver + Strategist | Publication | PENDING
Measurement Definition | Strategist / Measurement Owner + Client as needed | Analytics QA | PENDING
Strategic Fidelity QA | Strategist | Launch readiness | PENDING
Technical QA | Lead Developer / QA owner | Launch readiness | PENDING
Accepted Limitations | Project Lead + relevant client / specialist | Launch | PENDING
Production Launch | Authorized Human | Launch | PENDING

## Summary
QA Summary
Formula-driven overview. Formula counts derive from QA and issue tabs.
Metric | Formula / Result | Interpretation
Launch gates blocked |  | Any blocked launch gate prevents launch authorization.
Launch gates not tested |  | Not tested is not a pass.
Strategic Fidelity not tested |  | Implementation evidence still required.
Technical QA not tested |  | Technical evidence still required.
Open issues |  | Open items requiring resolution or explicit acceptance.
Blocking issues |  | Blocking issues must be resolved before launch.
Pending approvals |  | Human approvals still required.

## Change Log
Change Log
Revision history for the QA / Launch Readiness workbook.
Version | Date | Requested By | Tab / Area | Change | Status | Approved By
v1.0 | 2026-09-02 | SimpliCreative | All | Initial Gold Standard created from NuVue Foundation requirements; implementation observations intentionally left NOT TESTED — DEMO. | Issued for Human Review