## Read Me
NuVue — Launch Record & Post-Launch Validation
Gold-standard Foundation workbook for recording what actually launched and validating the live business-critical experience.
Purpose | Capture the approved production state, launch authorization, known accepted limitations, critical live validation, post-launch issues, and follow-up ownership.
Demo boundary | NuVue is a demonstration case. No live production deployment was provided. All live observations remain NOT VALIDATED — DEMO unless supported by actual evidence.
Difference from GS-FOUND-009 | GS-FOUND-009 asks whether the project is ready to launch. This workbook records what actually launched and whether the critical live experience worked after deployment.
Evidence rule | PASS requires production evidence such as a live URL, submission record, CRM record, analytics debug evidence, redirect response, search/indexing check, or documented human validation.
Accepted limitations | A limitation is not simply an unresolved issue. It must be explicitly accepted, have an owner, describe impact, and include follow-up when required.
Launch authority | AI may prepare and summarize this record. A human authorizes launch and approves the final production state.
Core rules
LAUNCH_READY != LAUNCHED
LIVE_STATE_REQUIRES_LIVE_EVIDENCE
PASS_REQUIRES_EVIDENCE
NOT_VALIDATED != PASS
ACCEPTED_LIMITATION_REQUIRES_HUMAN_APPROVAL
POST_LAUNCH_ISSUE_REQUIRES_OWNER
AI_MAY_DOCUMENT_LAUNCH
AI_MAY_NOT_AUTHORIZE_LAUNCH

## Launch Record
Launch Record
Authoritative production-state record. Demo values intentionally remain unresolved.
Field | Expected / Required | Production Value | Status | Evidence / Link | Owner | Approval / Notes
Client | NuVue | NuVue | RECORDED |  | Project Lead
Production URL | Final approved production URL | NOT VALIDATED — DEMO | NOT VALIDATED |  | Developer
Launch Date / Time | Actual production deployment timestamp | NOT VALIDATED — DEMO | NOT VALIDATED |  | Project Lead
Launch Version / Release | Production release identifier | NOT VALIDATED — DEMO | NOT VALIDATED |  | Developer
Launch Authorized By | Named authorized human | NOT VALIDATED — DEMO | BLOCKED |  | Authorized Human | Required before launch can be considered complete.
Final Site Architecture | Approved current architecture/version | GS-FOUND-008 remains demo / human review | BLOCKED |  | Strategist
Final Copy | Approved client copy/version | NOT VALIDATED — DEMO | NOT VALIDATED |  | Strategist + Client
Final Design | Approved production design/version | NOT VALIDATED — DEMO | NOT VALIDATED |  | Designer + Client
Known Accepted Limitations | All accepted limitations explicitly documented | See Accepted Limitations tab | NOT VALIDATED |  | Project Lead
Primary Ongoing Owner | Named post-launch owner / team | NOT VALIDATED — DEMO | NOT VALIDATED |  | Project Lead + Client
Note on C6: Populate only from actual production deployment evidence.

## Critical Live Checks
Critical Live Checks
Immediate production validation after launch. Only business-critical checks should live here.
Check ID | Area | Expected Live State | Observed Live State | Evidence | Status | Severity | Owner | Resolution / Notes
LC-001 | Homepage | Homepage loads correctly at final production URL; primary content and CTA hierarchy are visible. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Blocking | Developer / QA
LC-002 | Primary Navigation | Main navigation and mobile navigation route to approved destinations. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Blocking | Developer / QA
LC-003 | For My Team / For Myself | Audience routing works and remains clear on production. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Material | Strategist / QA
LC-004 | Primary Consultation CTA | Primary CTA routes to the correct consultation experience. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Blocking | Developer / QA
LC-005 | Consultation Form | Form submits successfully in production and shows correct confirmation. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Blocking | Developer / QA
LC-006 | CRM Routing | Production submission reaches correct CRM destination / owner with required fields. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Blocking | Developer + Client
LC-007 | Analytics | Required production events fire correctly with no obvious duplicate firing. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Material | Measurement Owner
LC-008 | Redirects | Priority moved/retired URLs resolve to approved destinations with correct response. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Material | Developer / QA
LC-009 | Search Accessibility | Production site is accessible to search engines according to approved launch state. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Blocking | Developer / SEO
LC-010 | Responsive Critical Flow | Homepage, navigation, forms, and priority paths work on approved mobile/desktop checks. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Material | Developer / QA
LC-011 | Proof / Claims | No placeholder, draft, unapproved claim, or synthetic demo language is visible. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Material | Strategist / QA
LC-012 | Error Monitoring | No obvious production-breaking 404, JS, form, or integration errors in critical path. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Blocking | Developer
Note on D5: Observed state must come from the live production environment, not staging or intended design.

## Forms & CRM
Forms & CRM
Validates live form submission, handoff, source context, ownership, and confirmation behavior.
Check ID | Form / Flow | Expected Behavior | Production Evidence | Status | CRM Destination / Owner | Required Fields / Data | Issue / Notes
FC-001 | Request a Consultation | Validates, submits, confirms, and routes to approved CRM flow. | NOT VALIDATED — DEMO | NOT VALIDATED | TBD — PRODUCTION | Name, company, role, email, industry, team size, challenge, timing; final list subject to approval
FC-002 | CSP Guarantee / Eligibility | Routes qualified interest into approved guarantee process if live. | NOT VALIDATED — DEMO | NOT VALIDATED | TBD — PRODUCTION | Eligibility fields / qualification context per approved terms
FC-003 | Self-Assessment | Starts/completes and routes according to approved scoring and next-step logic if live. | NOT VALIDATED — DEMO | NOT VALIDATED | TBD — PRODUCTION | Approved assessment inputs / score / result handling
FC-004 | Public Seminar / Registration | Completes transaction/registration and captures relevant company context. | NOT VALIDATED — DEMO | NOT VALIDATED | TBD — PRODUCTION | Registration + company context where approved
FC-005 | UTM / Source Capture | Preserves approved campaign and source context where technically available. | NOT VALIDATED — DEMO | NOT VALIDATED | CRM / analytics | utm_source, utm_medium, utm_campaign, page/source context where approved

## Analytics Validation
Analytics Validation
Confirms that live events exist and that event collection is not mistaken for business impact.
Event / Signal | Expected Trigger | Required Context | Observed Live State | Evidence | Status | Owner | Notes
buyer_path_select | For My Team / For Myself click | path; page | NOT VALIDATED — DEMO |  | NOT VALIDATED | Measurement Owner
consultation_cta_click | Consultation CTA click | location; page | NOT VALIDATED — DEMO |  | NOT VALIDATED | Measurement Owner
consultation_form_start | First meaningful interaction with consultation form | page; source context | NOT VALIDATED — DEMO |  | NOT VALIDATED | Measurement Owner
consultation_form_submit | Successful consultation submission | page; source context | NOT VALIDATED — DEMO |  | NOT VALIDATED | Measurement Owner
assessment_start | Assessment starts if launched | page; entry location | NOT VALIDATED — DEMO |  | NOT VALIDATED | Measurement Owner
assessment_complete | Assessment completes if launched | approved result / category context | NOT VALIDATED — DEMO |  | NOT VALIDATED | Measurement Owner
solution_select | Pillar click | pillar name | NOT VALIDATED — DEMO |  | NOT VALIDATED | Measurement Owner
guarantee_interest | Guarantee teaser / entry click | page; location | NOT VALIDATED — DEMO |  | NOT VALIDATED | Measurement Owner
industry_select | Industry selection | industry name | NOT VALIDATED — DEMO |  | NOT VALIDATED | Measurement Owner
CRM qualification | Qualified lead progression visible where supported | source; lifecycle / pipeline | NOT VALIDATED — DEMO |  | NOT VALIDATED | Client + Measurement Owner | Business impact requires downstream CRM evidence.

## Redirect Validation
Redirect Validation
Production validation for URL migration. Populate from final approved redirect map before launch.
Redirect ID | Existing URL | Approved Target | Expected Response | Observed Response | Status | Severity | Owner | Evidence / Notes
RV-001 | Sample only — use approved redirect map | Sample only — use approved target | 301 → final approved destination | NOT VALIDATED — DEMO | NOT VALIDATED | Material | Developer / QA | Do not treat sample row as production redirect.

## Search & Indexing
Search & Indexing
Immediate production checks for crawlability, indexing controls, canonicals, metadata, and sitemap availability.
Check ID | Check | Expected Live State | Observed Live State | Evidence | Status | Owner | Notes
SI-001 | Robots / Crawlability | Production crawlability matches approved launch state. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Developer / SEO
SI-002 | XML Sitemap | Production XML sitemap is accessible and reflects intended live URLs. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Developer / SEO
SI-003 | Canonical | Priority pages output correct canonical URL. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Developer / SEO
SI-004 | Indexing Directives | No unintended noindex/nofollow directives on launch-critical pages. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Developer / SEO
SI-005 | Meta Titles / Descriptions | Approved metadata appears in production. | NOT VALIDATED — DEMO |  | NOT VALIDATED | SEO / QA
SI-006 | Structured Data | Approved schema appears and validates where actual content supports it. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Developer / SEO
SI-007 | Search Console | Final property / sitemap submission and launch checks completed where in scope. | NOT VALIDATED — DEMO |  | NOT VALIDATED | SEO / Client

## Accessibility Follow-Up
Accessibility Follow-Up
Live follow-up for critical accessibility behavior after production deployment.
Check ID | Area | Launch-State Expectation | Observed Live State | Evidence | Status | Owner | Follow-Up / Notes
AF-001 | Keyboard / Focus | Critical live navigation, forms, and controls remain keyboard operable with visible focus. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Developer / QA
AF-002 | Forms | Labels, required states, errors, and confirmations remain usable in production. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Developer / QA
AF-003 | Contrast / Typography | Production CSS preserves approved contrast and readable type. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Designer / Developer
AF-004 | Images / Alt | Production content preserves intended alternative text behavior. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Content / QA
AF-005 | Motion | Any production motion respects reduced-motion requirements. | NOT VALIDATED — DEMO |  | NOT VALIDATED | Developer / QA

## Production Issues
Production Issues
Issues discovered during or immediately after launch. Use actual production evidence, owner, and retest state.
Issue ID | Detected At | Area | Issue | Severity | Status | Owner | Immediate Action | Resolution | Retest | Evidence / Link
PI-001 |  | Demo Boundary | No real NuVue production deployment was provided, so live-state validation cannot be completed. | Blocking | OPEN | Project Lead | Do not convert demo workbook to launch record without production evidence. |  | PENDING

## Accepted Limitations
Accepted Limitations
Accepted launch limitations require explicit human approval, owner, impact, and follow-up where needed.
Limitation ID | Area | Limitation | Impact | Reason Accepted | Owner | Follow-Up Required | Due Date | Approved By | Approval Date | Status
AL-001 | Demo Boundary | No production implementation exists for validation. | Cannot establish real launch readiness or live-state quality. | Demonstration artifact only. | Project Lead | Yes — replace with real production evidence before use as a live record. |  | NOT APPROVED |  | DEMO ONLY
Note on I5: Accepted limitations require explicit human approval. AI may document but not approve.

## Post-Launch Actions
Post-Launch Actions
Follow-up actions required after launch, including data validation, issue resolution, ownership transition, and baseline capture.
Action ID | Action | Trigger / Why | Owner | Due | Status | Evidence / Completion | Notes
PLA-001 | Validate critical live forms and CRM routing | Required immediately after production deployment. | Developer + Client |  | PENDING
PLA-002 | Validate required analytics events | Confirm production tracking before relying on data. | Measurement Owner |  | PENDING
PLA-003 | Validate priority redirects | Confirm migration behavior on high-value URLs. | Developer / QA |  | PENDING
PLA-004 | Confirm search accessibility / sitemap | Ensure production indexability matches approved state. | SEO / Developer |  | PENDING
PLA-005 | Capture post-launch baseline | Establish trustworthy baseline before improvement claims. | Measurement Owner |  | PENDING
PLA-006 | Close / accept production issues | Every material issue gets resolution or explicit acceptance. | Project Lead |  | PENDING
PLA-007 | Confirm ongoing ownership | Clarify SimpliCARE vs client/partner responsibilities. | Project Lead + Client |  | PENDING

## Approvals
Approvals
Human approval register for production launch and live-state acceptance.
Approval | Required Approver | Required Before / For | Current State | Approval Date | Evidence / Link | Notes
Production Launch Authorization | Authorized Human | Production deployment | PENDING
Final Production State | Project Lead + relevant specialists | Launch completion | PENDING
Accepted Limitations | Project Lead + relevant client/specialist | Launch completion | PENDING
Critical Live Validation | Developer / QA + Strategist where applicable | Post-launch closeout | PENDING
Ongoing Ownership Handoff | Project Lead + Client | Foundation closeout | PENDING

## Summary
Launch & Post-Launch Summary
Formula-driven summary of unresolved validation, production issues, and approvals.
Metric | Formula / Result | Interpretation
Launch Record blocked |  | Blocking launch-record states remain.
Critical checks not validated |  | Live evidence is still required.
Forms / CRM not validated |  | Critical conversion routing remains unverified.
Analytics not validated |  | Do not rely on post-launch reporting yet.
Production issues open |  | Open production issue(s) remain.
Pending approvals |  | Human approvals remain outstanding.
Pending post-launch actions |  | Required follow-up is not complete.

## Change Log
Change Log
Revision history for the Launch Record & Post-Launch Validation workbook.
Version | Date | Requested By | Tab / Area | Change | Status | Approved By
v1.0 | 2026-09-02 | SimpliCreative | All | Initial Gold Standard created for NuVue demonstration. Production states intentionally remain NOT VALIDATED — DEMO. | Issued for Human Review