## Read Me
Foundation Scoping Record — Northstar Demo
Internal commercial/scoping record. Foundation Scoping determines how an already-established strategy should be implemented. It is narrower than Blueprint and does not recreate strategy.
Purpose | Translate an approved strategic foundation into implementation scope, responsibilities, complexity, delivery economics, and a human-reviewable fixed-price recommendation.
When used | Direct-to-Foundation when strategy is already sufficiently established, or as the implementation/commercial scoping record after an approved Blueprint when a fixed Foundation scope still needs to be priced.
Demo boundary | Northstar previously served as the Blueprint demonstration. This workbook assumes the strategic direction is now approved and uses the full-scope Foundation scenario for illustration. It does not rewrite the prior Diagnostic route.
Important boundary | Foundation Scoping answers how approved strategy should be implemented. Material strategic unknowns route back to strategic review rather than being quietly resolved here.
Pricing boundary | Complexity, reference value, and delivery economics must validate one another. AI may calculate and recommend. All Foundation pricing requires human approval.
Client-facing boundary | The client normally receives one fixed Foundation investment. Complexity score, internal pricing band, reference values, labor cost, gross margin, and AI confidence remain internal.
Core rules
FOUNDATION_SCOPING != BLUEPRINT
IMPLEMENTATION_UNKNOWN != STRATEGIC_UNKNOWN
COMPLEXITY → REFERENCE VALUE → DELIVERY ECONOMICS
AI_RECOMMENDATION != HUMAN_PRICE_APPROVAL
CLIENT_FACING_PRICE = ONE_FIXED_INVESTMENT
INTERNAL_ECONOMICS_MUST_NOT_APPEAR_IN_PROPOSAL

## Scoping Summary
Scoping Summary
Internal executive view of implementation context, scope state, complexity, and commercial readiness.
Field | Current Demo State | Status | Source / Basis | Owner | Decision / Action | Client-Facing?
Entry Path | Approved Blueprint → Foundation Scoping | DEMO ASSUMPTION | Northstar demo sequence | Strategist | Use approved Blueprint as strategic source. | No
Business Objective | Increase qualified corporate leadership conversations and improve visibility into marketing contribution. | APPROVED FOR DEMO | Approved Blueprint scenario | Client + Strategist | Preserve through implementation. | Yes
Website Objective | Support corporate buyer evaluation, proof, routing, and meaningful conversion while retaining individual learner path. | APPROVED FOR DEMO | Approved Blueprint scenario | Strategist | Preserve through architecture and UX. | Yes
Primary Buyer | Corporate leadership / sales / L&D decision-makers; individual professionals secondary. | APPROVED FOR DEMO | Approved Blueprint scenario | Strategist | Use for page roles and CTA logic. | Yes
Implementation Variant | Full custom SimpliFoundation | DEMO ASSUMPTION | Full-scope proposal scenario | Commercial Lead | Validate final scope before pricing. | Yes
Strategic Unknowns | None assumed material for demo. | HUMAN REVIEW | Must be validated before Foundation bypass / activation. | Strategist | Escalate any material strategic unknown. | No
Implementation Unknowns | Final page count, component count, migration volume, exact integrations, final event taxonomy, final stakeholder cadence. | OPEN | Scoping inputs incomplete | Project Lead | Resolve before fixed-price approval where material. | No
Complexity Score | See Complexity Score tab. | FORMULA |  | Commercial Lead | Validate scored assumptions. | No
Reference Value | See Deliverable Validation tab. | FORMULA / INTERNAL |  | Commercial Lead | Validate included deliverables. | No
Delivery Economics | See Delivery Economics tab. | INCOMPLETE |  | Commercial Lead | Populate current role/cost assumptions. | No
Recommended Fixed Investment | See Pricing Recommendation tab. | BLOCKED UNTIL ECONOMICS + HUMAN APPROVAL |  | Commercial Approver | Approve one fixed investment. | Yes

## Strategic Foundation
Strategic Foundation Validation
This tab confirms whether strategy is sufficient for Foundation. It does not redevelop strategy.
Strategic Input | Required State | Demo State | Status | Evidence / Source | Remaining Unknown | Action
Business Objective | Approved | Qualified corporate growth + clearer marketing contribution. | APPROVED FOR DEMO | Approved Blueprint scenario |  | Preserve
Website Objective | Approved | Support evaluation, proof, routing, conversion, and measurement. | APPROVED FOR DEMO | Approved Blueprint scenario |  | Preserve
ICP / Primary Buyers | Approved | Corporate decision-makers primary; individual learner secondary. | APPROVED FOR DEMO | Approved Blueprint scenario |  | Preserve
Positioning | Sufficiently established | Executive learning partner with faculty depth, customization, business relevance, and enterprise credibility. | APPROVED FOR DEMO | Approved Blueprint scenario |  | Preserve
Differentiation / UVP | Sufficiently established | Differentiation is stronger in sales conversation than current digital experience. | APPROVED FOR DEMO | Approved Blueprint scenario |  | Translate into proof + messaging
Core Offers | Defined | Corporate programs + individual/seminar pathways. | APPROVED FOR DEMO | Approved Blueprint scenario | Exact product inventory for final architecture. | Implementation detail
Messaging Direction | Sufficiently established | Corporate-first, proof-aware, decision-supporting narrative. | APPROVED FOR DEMO | Approved Blueprint scenario |  | Preserve
Buyer Journey | Sufficiently established | Awareness/evaluation occurs across referrals, events, PR, faculty visibility, social/content, then website evaluation. | APPROVED FOR DEMO | Approved Blueprint scenario | Final page-by-page routing. | Implementation detail
Conversion Objectives | Defined | Qualified corporate consultation + lower-friction supporting paths. | APPROVED FOR DEMO | Approved Blueprint scenario | Final form/CRM fields. | Implementation detail
Success Criteria | Defined enough to scope | Meaningful buyer progression + more trustworthy measurement. | APPROVED FOR DEMO | Approved Blueprint scenario | Exact post-launch baseline and targets. | Implementation detail
Material Strategic Unknowns | None that would materially change implementation scope | None assumed for demo. | HUMAN REVIEW | Requires strategist confirmation before pricing. | If discovered, route back to strategic review. | Gate

## Implementation Scope
Implementation Scope
Full-scope demo of Foundation implementation requirements. Human review determines the final SOW.
Workstream | In Scope? | Implementation Requirement | Known Quantity / Level | Open Scoping Question | Client Responsibility | SimpliCreative Responsibility | Status | Strategic Impact if Changed
Messaging & Editorial | Yes | Website Messaging & Content Blueprint, Brand Voice & Editorial Guide, claim/evidence controls, page-level messaging. | Meaningful development | What existing messaging assets are already approved? | Provide current materials, proof, approvals. | Lead development, synthesis, drafting, review. | DEMO ASSUMPTION | High
Information Architecture | Yes | Integrated site architecture, navigation, buyer intent, URLs, redirects, metadata/schema. | Multiple journeys/templates | Final page inventory and retirement/migration count? | Approve architecture and URL changes. | Lead architecture and integrated workbook. | DEMO ASSUMPTION | High
Website Content | Yes | Page briefs, production copy, proof placement, CTA logic, editorial review. | Significant work | Final page/template count and content reuse? | Provide SME access, proof, timely approvals. | Draft/edit approved website content. | OPEN | High
UX / Conversion | Yes | Corporate-first routing, individual path, CTA hierarchy, forms, qualification logic. | Multiple paths | Exact lower-friction conversion tools? | Validate sales/CRM requirements. | Lead UX/conversion requirements. | OPEN | High
Custom Visual Design | Yes | Custom homepage, core templates, reusable components, responsive experience. | Larger/custom | How many unique core templates/components? | Approve design direction. | Lead design system and page/template design. | OPEN | Medium
WordPress Development | Yes | Custom WP implementation, reusable component system, marketer-safe controls. | Advanced custom | Hosting/technical constraints? | Provide access and technical requirements. | Build/configure approved implementation. | OPEN | Medium
Forms & CRM | Yes | Consultation/qualification forms, source context, routing, CRM integration. | Multiple workflows | Exact fields, lifecycle stages, routing rules? | Provide HubSpot/process ownership. | Implement approved forms/integration. | OPEN | High
Analytics & Measurement | Yes | GA4/GTM, custom events/funnels, conversion tracking, baseline/reporting setup. | Custom events/funnels | Current property/container health and event taxonomy? | Provide access and reporting needs. | Implement/validate measurement. | OPEN | High
SEO | Yes | Metadata, internal linking, on-page SEO, crawl/indexing, migration protection. | Significant | Current ranking/URL equity priorities? | Provide Search Console/access. | Implement approved SEO architecture. | OPEN | Medium
AEO / GEO | Yes | Entity clarity, answer-focused content, authority cues, structured content. | Significant | Priority AI/recommendation research themes? | Provide SME/proof context. | Implement approved AEO/GEO requirements. | OPEN | Medium
Schema | Yes | Page-specific schema where actual content supports it. | Multiple types | Final page eligibility? | Provide accurate factual/entity data. | Implement valid structured data. | OPEN | Low
Accessibility | Yes | Accessibility review + standard remediation + human validation. | Meaningful remediation | Any client/regulatory standard above project baseline? | Provide known requirements. | Review/remediate within approved scope. | OPEN | Medium
Content Migration | Yes | Approved migration, cleanup, mapping, and redirects. | Extensive | Exact page/file count? | Identify content to retain/archive. | Plan and perform approved migration. | OPEN | Medium
Integrations | Yes | Approved third-party integrations required by experience. | Several | Any custom API/ERP beyond standard tools? | Provide credentials/owners. | Implement approved integrations. | OPEN | High
Technical Performance | Yes | Asset/script/performance/maintainability production controls. | Custom site | Hosting and third-party constraints? | Approve hosting/access decisions. | Optimize within implementation. | OPEN | Medium
QA / Launch | Yes | Strategic Fidelity QA, Technical QA, launch, live validation, handoff. | Full | Approved browser/device/QA scope? | Participate in final approvals. | Lead QA/launch documentation. | OPEN | Medium

## Responsibility Map
Responsibility Map
Clarifies client, SimpliCreative, and partner ownership before scope and price are approved.
Area | SimpliCreative | Northstar | Existing / Other Partner | Decision Needed | Status | Commercial Impact
Strategy | Implement approved strategy; escalate material strategic gaps. | Approve material changes. | None assumed. | Confirm strategic approver. | OPEN | High
Content | Draft/edit agreed website copy and page requirements. | Provide proof, SMEs, factual review, approvals. | Potential internal content owner. | Confirm page/content ownership split. | OPEN | High
Design | Lead approved custom UX/visual design. | Review/approve. | None assumed. | Confirm stakeholder review group. | OPEN | Medium
Development | Build/configure approved WordPress experience. | Provide access / infrastructure decisions. | Hosting/IT may participate. | Confirm hosting/IT owner. | OPEN | Medium
CRM / MarTech | Implement agreed forms/integrations. | Own CRM governance and sales process. | HubSpot admin/partner TBD. | Confirm technical owner and responsibilities. | OPEN | High
Analytics | Implement approved web tracking. | Own business process/data discipline. | Existing analytics support TBD. | Confirm ongoing reporting owner. | OPEN | Medium
SEO/AEO/GEO | Implement approved discoverability requirements. | Provide expertise/proof/content approvals. | Existing SEO partner TBD. | Confirm overlap / handoff if partner exists. | OPEN | Medium
Migration | Plan/execute approved migration. | Decide retain/retire/archive and provide content. | IT/content partner TBD. | Confirm migration support. | OPEN | Medium
Launch | Lead deployment/QA within approved technical scope. | Authorize launch and approve final state. | Hosting/IT may assist. | Confirm launch authority. | OPEN | High

## Dependencies & Risks
Dependencies & Risks
Material scope, delivery, and pricing dependencies that must be resolved or explicitly accepted.
ID | Dependency / Risk | Type | Impact if Unresolved | Owner | Required Resolution | Status | Pricing / Scope Effect
DR-001 | Final page / template inventory | Scope dependency | Copy, design, dev, migration, and QA volume remain uncertain. | Strategist + Client | Approve architecture scope. | OPEN | Potential material
DR-002 | Migration volume | Delivery dependency | Content migration effort cannot be estimated reliably. | Client + Project Lead | Inventory current content/files. | OPEN | Potential material
DR-003 | HubSpot workflows / lifecycle | Integration dependency | CRM scope and measurement complexity remain uncertain. | Client CRM Owner | Document current state and target requirements. | OPEN | Material
DR-004 | Final analytics event taxonomy | Measurement dependency | Build and QA effort remain uncertain. | Measurement Owner | Approve events/funnels. | OPEN | Moderate
DR-005 | Proof / claim permissions | Content dependency | Copy and proof modules may need rework if evidence is unavailable. | Client | Provide approved evidence/permissions. | OPEN | Moderate
DR-006 | Custom APIs / ERP | Technical risk | Could move integrations from standard to complex. | Client IT | Confirm whether any custom API/ERP work is required. | OPEN | Automatic human review
DR-007 | Stakeholder count / governance | Governance risk | More than five active stakeholders triggers review. | Project Lead | Confirm active approvers/reviewers. | OPEN | Potential material
DR-008 | Timeline pressure | Delivery risk | Compressed schedule can increase delivery cost/risk. | Client + Project Lead | Confirm desired launch window. | OPEN | Potential material
DR-009 | Accessibility requirements | Compliance / scope risk | Higher-complexity requirements may expand remediation/testing. | Client | Confirm required standard/regulatory context. | OPEN | Potential material

## Complexity Score
Foundation Complexity Score
15-dimension internal score. Demo inputs are illustrative assumptions and require human validation.
Dimension | Simple (1) | Moderate (2) | Complex (3) | Demo Score | Demo Basis | Human Review
Storytelling & Messaging | Apply/refine | Meaningful development | Major strategic development | 2 | Meaningful development assumed; strategy already approved. | REVIEW
Information Architecture | Straightforward | Multiple journeys/templates | Complex architecture | 2 | Corporate + individual paths and multiple templates. | REVIEW
Content | Mostly ready | Significant work/migration | Extensive creation/migration | 3 | Full-scope demo assumes significant creation + extensive migration. | REVIEW
Design System | Standard | Larger/custom | Advanced/custom | 2 | Custom design system assumed. | REVIEW
CMS | Standard | Complex structures | Advanced workflows/data | 3 | Advanced custom component/CMS system assumed. | REVIEW
Conversion | Straightforward | Multiple paths | Complex routing/qualification | 2 | Corporate + individual + assessment/guarantee paths. | REVIEW
CRM / MarTech | Standard | Multiple workflows | Significant architecture | 3 | HubSpot workflows and routing are meaningful unknowns. | REVIEW
Analytics | Standard | Custom events/funnels | Cross-system measurement | 3 | Custom events + CRM opportunity linkage. | REVIEW
SEO/AEO/GEO | Foundational | Significant | Broad/complex | 2 | Significant implementation across full architecture. | REVIEW
Accessibility | Standard | Meaningful remediation | High-complexity requirements | 2 | Meaningful remediation assumed; no special regulatory scope yet. | REVIEW
Integrations | Few/standard | Several | API/ERP/custom | 2 | Several integrations assumed; API/ERP unresolved. | REVIEW
Stakeholders | 1–2 | 3–5 | Multiple departments | 2 | Cross-functional approval group assumed. | REVIEW
Brands / Markets | One | Multiple segments | Multiple brands/regions/languages | 1 | One organization/market assumed. | REVIEW
Timeline | Normal | Some pressure | Materially compressed | 1 | Normal timeline assumed until client confirms otherwise. | REVIEW
Partner Coordination | Minimal | 1–2 partners | Multiple partners | 2 | Potential hosting/IT/CRM/SEO coordination. | REVIEW
TOTAL COMPLEXITY SCORE
CLASSIFICATION
INTERNAL PRICING BAND
Note on E5: Blue score inputs are demo assumptions and require human validation before pricing.

## Deliverable Validation
Deliverable Reference-Value Validation
Internal validation only. Reference values do not make Foundation an à la carte menu and do not appear in client proposals.
Deliverable / Workstream | Included? | Internal Reference Value | Qty | Extended Reference Value | Notes | Review
Storytelling & Messaging Architecture | Yes | 7500 | 1 |  | Bundled / custom | REVIEW
Positioning / UVP refinement | No | 5000 | 0 |  | Not assumed necessary after approved Blueprint. | REVIEW
Website Strategy + IA | Yes | 5000 | 1 |  | Integrated architecture included. | REVIEW
Buyer Journey / Conversion Architecture | Yes | 4000 | 1 |  | Multiple buyer paths. | REVIEW
AEO / AI Recommendation Strategy | Yes | 4000 | 1 |  | Foundation implementation context. | REVIEW
SEO / Discoverability Architecture | Yes | 4000 | 1 |  | Foundation implementation context. | REVIEW
Measurement Architecture | Yes | 3500 | 1 |  | Measurement / CRM design. | REVIEW
Custom Homepage UX + Design | Yes | 6000 | 1 |  | Custom homepage. | REVIEW
Custom Core Page Template | Yes | 2500 | 4 |  | Illustrative quantity; human review. | REVIEW
Secondary/Reused Page Layout | Yes | 1000 | 8 |  | Illustrative quantity; human review. | REVIEW
Custom Landing Page | No | 2500 | 0 |  | Not assumed unless campaign-specific need emerges. | REVIEW
WordPress Development Foundation | Yes | 10000 | 1 |  | Bundled development foundation. | REVIEW
Advanced CMS / Component System | Yes | 5000 | 1 |  | Advanced component system assumed. | REVIEW
Standard Form Integration | Yes | 750 | 2 |  | Illustrative two forms. | REVIEW
Advanced Form | Yes | 1500 | 1 |  | Illustrative guarantee/qualification flow. | REVIEW
Standard CRM Integration | Yes | 2500 | 1 |  | HubSpot integration. | REVIEW
Advanced CRM Workflow | Yes | 4000 | 2 |  | Illustrative quantity; human review. | REVIEW
GA4 + GTM Foundational Setup | Yes | 2000 | 1 |  | Measurement foundation. | REVIEW
Custom Event / Conversion Setup | Yes | 500 | 10 |  | Illustrative event count; human review. | REVIEW
Executive Measurement Dashboard | Yes | 3500 | 1 |  | Included in full-scope demo. | REVIEW
Foundational On-Page SEO | Yes | 2500 | 1 |  | Implementation baseline. | REVIEW
AEO Implementation | Yes | 3500 | 1 |  | Implementation baseline. | REVIEW
Accessibility Review + Standard Remediation | Yes | 2500 | 1 |  | Higher complexity may increase. | REVIEW
Standard Third-Party Integration | Yes | 1000 | 3 |  | Illustrative quantity. | REVIEW
Complex/API Integration | No | 3500 | 0 |  | Not assumed unless DR-006 resolves yes. | REVIEW
Content Migration, first 20 pages | Yes | 2500 | 1 |  | Included as base migration. | REVIEW
Additional Migration | Yes | 125 | 40 |  | Illustrative additional pages; human review. | REVIEW
TOTAL INTERNAL REFERENCE VALUE
Note on C5: Internal reference value from current pricing source. Do not expose in client proposal.

## Delivery Economics
Delivery Economics
Internal cost and margin validation. Blue cells are human/commercial inputs. Do not expose this tab in client-facing proposals.
Role / Cost | Estimated Hours / Qty | Loaded Rate / Unit Cost | Extended Cost | Source / Basis | Status | Notes
Strategist / Account Lead |  |  |  | Current internal labor model required | PENDING
Content / Messaging |  |  |  | Current internal labor model required | PENDING
UX / Design |  |  |  | Current internal labor model required | PENDING
Development |  |  |  | Current internal labor model required | PENDING
SEO / AEO / Analytics |  |  |  | Current internal labor model required | PENDING
Project Management / QA |  |  |  | Current internal labor model required | PENDING
Contractors |  |  |  | Current contractor quotes / assumptions | PENDING
Software / Project Expenses |  |  |  | Project-specific costs | PENDING
SUBTOTAL DELIVERY COST
CONTINGENCY %
RISK-ADJUSTED DELIVERY COST

## Pricing Recommendation
Foundation Pricing Recommendation
Complexity, reference value, and delivery economics must validate one another before one fixed investment is recommended.
Control | Value | Status | Interpretation | Human Decision | Client-Facing?
Complexity Score |  | FORMULA | Internal complexity signal. |  | No
Complexity Classification |  | FORMULA | Internal classification. |  | No
Internal Pricing Band |  | FORMULA | Guardrail, not client price. |  | No
Deliverable Reference Value |  | FORMULA | Validates scope/responsibility; not line-item client pricing. |  | No
Risk-Adjusted Delivery Cost |  | BLOCKED UNTIL INPUTS | Delivery economics cannot validate price until costs are populated. |  | No
Approved Margin Floor |  | HUMAN INPUT | Current commercial policy required. |  | No
Margin-Supporting Minimum Price |  | FORMULA AFTER INPUT | Price needed to meet approved margin floor. |  | No
Recommended Fixed Investment |  | BLOCKED | AI may recommend only after all three controls reconcile. |  | Yes
Pricing Review Result |  | BLOCKED | PASS / PRICING REVIEW REQUIRED. |  | No
Human Approver |  | PENDING | All Foundation pricing requires human approval. |  | No
Final Approved Price |  | PENDING | One client-facing fixed investment. |  | Yes
Note on B15: Final Foundation price requires explicit human commercial approval.

## Approval Gate
Foundation Scoping Approval Gate
Foundation cannot move to a final proposal until material scoping and commercial gates are approved.
Gate | Required State | Demo State | Status | Owner | Evidence / Decision | Blocks Proposal?
Strategic Foundation | No unresolved material strategic unknowns. | Human review required. | PENDING | Strategist |  | Yes
Implementation Scope | Required deliverables and responsibilities sufficiently defined. | Several open quantities/dependencies. | PENDING | Project Lead + Specialists |  | Yes
Architecture / Content Volume | Page/template/migration scope understood enough to price. | Not finalized in demo. | PENDING | Strategist + Content Lead |  | Yes
Technical / Integration Scope | CMS, CRM, forms, integrations, accessibility, migration, performance understood enough to price. | Several open items. | PENDING | Technical Lead |  | Yes
Stakeholders / Partners | Active approvers and partner responsibilities defined. | Open. | PENDING | Project Lead |  | Yes
Timeline | Delivery window sufficiently known. | Open. | PENDING | Project Lead + Client |  | Yes
Complexity Score | Human-reviewed scoring complete. | Demo assumptions only. | PENDING | Commercial Lead |  | Yes
Reference Value | Included deliverables/quantities human-reviewed. | Demo assumptions only. | PENDING | Commercial Lead |  | Yes
Delivery Economics | Hours/costs/contingency populated. | Not populated. | BLOCKED | Commercial Lead |  | Yes
Margin Validation | Approved margin floor passes. | Cannot calculate yet. | BLOCKED | Commercial Approver |  | Yes
Fixed Investment | One price recommended and approved. | Not available. | BLOCKED | Authorized Human |  | Yes
Proposal Ready | All required gates above approved. | No. | BLOCKED | Commercial Approver |  | Yes

## Change Log
Change Log
Revision history for the Foundation Scoping Record.
Version | Date | Requested By | Area | Change | Status | Approved By
v1.0 | 2026-09-03 | SimpliCreative | All | Initial Gold Standard created for Northstar full-scope Foundation scoping demonstration. Complexity/reference-value assumptions are illustrative; delivery economics and fixed price intentionally remain unresolved. | Issued for Human Review